## Sheet1
Equipment | PO No. | Delivery Terms | Budget | PPMP | # of Signatures | # of Pages | # of days till next process (days) | PR + Attachments (i.e, Bid form) | # of Signatures | # of Pages | # of days till next process (days) | Pre-Bid (Pre-posting) | # of Signatures | # of Pages | # of days till next process (days) | Opening of Bids | # of Signatures | # of Pages | # of days till next process (days) | Post-Qualification | # of Signatures | # of Pages | # of days till next process (days) | NOA | # of Signatures | # of Pages | # of days till next process (days) | PO | # of Signatures | # of Pages | # of days till next process (days) | PO Approval | # of Signatures | # of Pages | # of days till next process (days) | PO Supplier Signature | # of Signatures | # of Pages | # of days till next process (days) | Delivery | # of Signatures | # of Pages | # of days till next process (days) | DV Processing | # of Signatures | # of Pages | # of days till next process (days) | DV Approval | # of Signatures | # of Pages | # of days till next process (days) | OR/CR Request | # of Signatures | # of Pages | # of days till next process (days) | Check Releasing | # of Signatures | # of Pages | # of days till next process (days) | Lead Time from PPMP to Delivery (days) | Total No. of Signatures
Airconditioning Systems | UPD-16-06-0797 | 20 | 193388.88 | 2016-04-08 | 2 | 2 | 42 | 2016-05-20 | 4 | 3 | 6 | 2016-05-26 | 3 | 4 | 13 | 2016-06-08 | 3 | 3 | 8 | 2016-06-16 | 5 | 7 | 4 | 2016-06-20 | 5 | 2 | 0 | 2016-06-20 | 2 | 1 | 0 | 2016-06-20 | 1 | 1 | 0 | 2016-06-20 | 1 | 1 | 31 | 2016-07-21 | 2 | 2 | 19 | 2016-08-09 | 10 | 4 | 36 | 2016-09-14 | 4 | 2 | 2 | 2016-09-16 | 1 | 1 | 3 | 2016-09-19 | 1 | 1 | 0 | 164 | 44
Heating Mantle | UPD-16-12-1684 | 30 | 90000 | 2016-11-11 | 2 | 2 | 3 | 2016-11-14 | 9 | 1 | 3 | 2016-11-17 | 2 | 4 | 7 | 2016-11-24 | 1 | 4 | 8 | 2016-12-02 | 9 | 1 | 19 | 2016-12-21 | 10 | 3 | 0 | 2016-12-21 | 1 | 1 | 0 | 2016-12-21 | 1 | 1 | 0 | 2016-12-28 | 1 | 1 | 77 | 2017-03-15 | 1 | 3 | 1 | 2017-03-16 | 7 | 3 | 63 | 2017-05-18 | 2 | 2 | 4 | 2017-05-22 | 1 | 1 | 3 | 2017-05-25 | 1 | 1 | 0 | 188 | 48
Mode-locked picosecond Nd: YAG Laser | UPS SPMO 2016-033 | 240 | 3700000 | 2016-05-02 | 2 | 2 | 15 | 2016-03-17 | 4 | 3 | 15 | 2016-04-01 | 0 | 4 | 41 | 2016-05-12 | 6 | 1 | 7 | 2016-05-19 | 6 | 8 | 4 | 2016-05-23 | 5 | 2 | 31 | 2016-06-14 | 2 | 4 | 12 | 2016-06-26 | 2 | 4 | 30 | 2016-07-26 | 2 | 4 | 310 | 2017-06-01 | 1 | 3 | 30 | 2017-08-01 | 10 | 3 | 100 | 2017-11-09 | 2 | 2 | 1 | 2017-11-10 | 3 | 2 | 1 | 2017-11-11 | 2 | 1 | 0 | 597 | 47
Laser Table & Table Connector | UPD-17-04-0334 | 84 | 811359 | 2017-02-14 | 3 | 1 | 1 | 2017-02-15 | 9 | 1 | 20 | 2017-03-03 | 2 | 4 | 10 | 2017-03-16 | 1 | 4 | 5 | 2017-03-21 | 9 | 1 | 13 | 2017-04-03 | 10 | 3 | 8 | 2017-04-11 | 1 | 1 | 6 | 2017-04-17 | 1 | 1 | 1 | 2017-04-07 | 1 | 1 | 55 | 2017-06-01 | 1 | 3 | 11 | 2017-07-12 | 7 | 3 | 26 | 2017-08-07 | 2 | 2 | 1 | 2017-08-08 | 3 | 2 | 1 | 2017-08-09 | 2 | 1 | 0 | 158 | 52
Orbital Shaker | UPD-17-06-0567 | 30 | 386400 | 2017-02-04 | 3 | 2 | 62 | 2017-04-17 | 9 | 3 | 8 | 2017-04-25 | 2 | 4 | 9 | 2017-05-04 | 1 | 3 | 4 | 2017-05-08 | 9 | 1 | 10 | 2017-05-18 | 10 | 3 | 40 | 2017-06-27 | 1 | 1 | 0 | 2017-06-27 | 1 | 1 | 8 | 2017-07-05 | 1 | 1 | 0 | 2017-07-05 | 1 | 3 | 6 | 2017-07-11 | 11 | 3 | 32 | 2017-08-12 | 2 | 2 | 3 | 2017-08-15 | 3 | 2 | 6 | 2017-11-21 | 2 | 1 | 0 | 188 | 56
Heating and Drying Oven and Chiller | UPD-17-060511 | 63 | 257000 | 2017-02-14 | 3 | 1 | 1 | 2017-05-02 | 9 | 1 | 9 | 2017-05-11 | 2 | 4 | 7 | 2017-05-18 | 1 | 4 | 7 | 2017-05-25 | 9 | 1 | 7 | 2017-06-01 | 10 | 3 | 12 | 2017-06-13 | 1 | 1 | 0 | 2017-06-13 | 1 | 1 | 3 | 2017-06-16 | 1 | 1 | 98 | 2018-09-22 | 1 | 3 | 3 | 2017-09-25 | 7 | 3 | 81 | 2017-11-14 | 2 | 2 | 2 | 2017-11-16 | 3 | 2 | 4 | 2017-11-20 | 2 | 1 | 0 | 234 | 52
Computer Server | UPD-18-05-555 | 60 | 487500 | 2018-02-07 | 2 | 1 | 1 | 2018-02-08 | 6 | 1 | 22 | 2018-03-02 | 2 | 4 | 20 | 2018-03-22 | 1 | 2 | 12 | 2018-04-03 | 8 | 1 | 65 | 2018-06-07 | 10 | 3 | 0 | 2018-06-07 | 1 | 1 | 0 | 2018-06-07 | 1 | 1 | 5 | 2018-06-12 | 1 | 1 | 37 | 2018-07-19 | 1 | 3 | 8 | 2018-07-26 | 7 | 3 | 54 | 2018-09-18 | 2 | 2 | 3 | 2018-09-21 | 3 | 2 | 4 | 2018-09-25 | 2 | 1 | 0 | 231 | 47
Chlorophyll Meter | UPD 18-12-1528 | 60 | 258000 | 2018-06-22 | 2 | 1 | 108 | 2018-10-08 | 6 | 3 | 17 | 2018-10-18 | 2 | 3 | 21 | 2018-11-08 | 1 | 2 | 20 | 2018-11-28 | 8 | 5 | 16 | 2018-12-14 | 9 | 4 | 0 | 2018-12-14 | 1 | 1 |  | 2018-12-14 | 1 | 1 | 3 | 2018-12-17 | 1 | 1 | 44 | 2019-01-30 | 1 | 2 | 19 | 2019-02-18 | 9 | 3 | 35 | 2019-03-25 | 2 | 3 | 2 | 2019-03-27 | 3 | 2 | 2 | 2019-03-29 | 2 | 1 | 0 | 287 | 48
High End Laptops and Server | UPD 19-04-0643 | 30 | 896280 | 2018-06-22 | 2 | 1 | 146 | 2018-11-15 | 6 | 3 | 16 | 2018-12-01 | 2 | 3 | 37 | 2019-01-07 | 1 | 2 | 11 | 2019-01-18 | 8 | 5 | 101 | 2019-04-29 | 9 | 4 | 0 | 2019-04-29 | 1 | 1 | 0 | 2019-04-29 | 1 | 1 | 1 | 2019-04-30 | 1 | 1 | 14 | 2019-05-14 | 1 | 2 | 1 | 2019-05-15 | 9 | 3 | 58 | 2019-07-12 | 2 | 3 | 2 | 2019-07-15 | 3 | 2 | 3 | 2019-07-17 | 2 | 1 | 0 | 390 | 48
Computer Workstation | UPD-19-10-1342 | 30 | 268485 | 2019-09-13 | 3 | 1 | 1 | 2019-09-16 | 6 | 3 | 15 | 2019-10-01 | 2 | 3 | 13 | 2019-10-14 | 4 | 5 | 4 | 2019-10-18 | 2 | 6 | 6 | 2019-10-24 | 9 | 4 | 0 | 2019-10-24 | 1 | 1 |  | 2019-10-29 | 1 | 1 | 7 | 2019-11-05 | 1 | 1 | 14 | 2019-11-20 | 1 | 3 | 259 | 2020-03-06 | 9 | 3 | [13 empty] | 319 | 39
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
[60 empty] | 0 | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0